## EXAMPLE Development Plan
Bowls Support Fund - Delivery Plan (APRIL-DECEMBER 26)
Phase One: APRIL-MAY 2026 |  |  |  | Phase Two: JUNE-AUGUST 2026 |  |  |  | Phase Three: SEPTEMBER 2026
Actions | Responsibility | Date To Be Completed By | Status | Actions | Responsibility | Date To Be Completed By | Status | Actions | Responsibility | Date To Be Completed By | Status
For Example: Purchase all required equipment | Treasurer | 2026-04-01 | ON TRACK | For Example: Launch new sessions utilising the new equipment with the following targetted group… | Chair | 2026-06-01 | COMPLETE | For Example: Review and report back on uptake of additional session from target group and the impact of the new equipment / sessions | Full Committee | 2026-09-01 | OUTSTANDING
For Example: Begin coaching qualification process for 3 club members via… (name NGB) | Secretary | 2026-04-01 | OUTSTANDING | For Example: Have 3 coaches further upskilled through… (name NGB) | Secretary | 2026-06-01 | OUTSTANDING | For Example: Have an established network of qualified coaches, and expanded volunteer network for club sustainability | Secretary | 2026-09-01 | OUTSTANDING
For Example: Strengthen outreach by creating an offer with local schools and Family Hubs. | Chair | 2026-04-01 | OUTSTANDING | For Example: Introduce Coventry Schools Games events into the venue, focussed initially on local schools. | Chair | 2026-06-01 | OUTSTANDING | For Example: Have regular Schools Games events hosted in the Gym - with local schools. Begin exploring welcoming in wider reach of schools. | Chair | 2026-09-01 | OUTSTANDING
Supporting information:

## EXAMPLE Budget
Prioritisation | Project Detailed Budget | Cost
| Bowls equipment | 0
| Community engagement | 0
| Coaching | 0
| Minor facility adaptaions | 0
| Accessibility enhancements | 0
TOTAL COSTS: |  | 0
Supporting information: